## Daily report drilling
DAILY TEST-PUMPING PROGRESS REPORT
[7 empty] | DATE: | 2025-10-01
CLIENT: |  |  | LMC |  |  |  | SHIFT [D/N] | Day
RIG No_1 |  | PROJECT/SITE AREA: |  | MALUNDWE |  | SHIFT START: | 6:00 | SHIFT END: | 18:00
|  | Control BH_ID: | KMDW09 | OBS_BH_1_ID: | KMM01 | OBS_BH_2_ID: | 9 | OBS_BH_3_ID: | 98
Activity |  |  |  |  | Time |  |  | Chargeable [Tick]
[5 empty] | From (Hrs) | To (Hrs) | Total Hrs | Yes | No
1 | ARRIVAL ON SITE |  |  |  | 6:00 | 6:50 |  |  | X
2 | TOOLBOX TALK |  |  |  | 6:50 | 7:20 |  |  | X
3 | FLRA |  |  |  | 7:20 | 7:30 |  |  | X
4 | CONSTANT DISCHARGE TEST PUMPING |  |  |  | 7:30 | 10:30 |  | X
5 | WATER SAMPLE COLLECTION |  |  |  | 10:30 | 10:35 |  | X
6 | CONSTANT DISCHARGE TEST PUMPING |  |  |  | 10:35 | 18:00 |  | X
7
8
9
10
Personnel on duty
# | [Full Names] |  |  |  | Hrs Worked | [Full Names] |  |  | Hrs Worked
1 | DESMOND CHISENGA |  |  |  | 12
2 | FRIDAH KANYENZE |  |  |  | 12
3 | DALITSO SAKALA |  |  |  | 12
4 | MOFFAT DAKA |  |  |  | 12
5
| SHIFT: | NIGHT | SHIFT START: |  | 18:00 |  | SHIFT END: | 6:00
Activity |  |  |  |  | Time |  |  | Chargeable [Tick]
[5 empty] | From (Hrs) | To (Hrs) | Total Hrs | Yes | No
1 | ARRIVAL ON SITE |  |  |  | 18:00 | 18:05 |  |  | X
2 | TOOLBOX TALK |  |  |  | 18:05 | 18:15 |  |  | X
3 | FLRA |  |  |  | 18:15 | 18:20 |  |  | X
4 | CONSTANT DISCHARGE TEST PUMPING |  |  |  | 18:20 | 22:30 |  | X
5 | WATER SAMPLE COLLECTION |  |  |  | 22:30 | 22:35 |  | X
6 | CONSTANT DISCHARGE TEST PUMPING |  |  |  | 22:35 | 0:00 |  | X
7 | CONSTANT DISCHARGE TEST PUMPING |  |  |  | 0:00 | 6:00 |  | X
8
9
10
Personnel on duty
# | [Full Names] |  |  |  | Hrs Worked | [Full Names] |  |  | Hrs Worked
1 | LACKY KANGWANDA |  |  |  | 12
2 | GILERT KASHITO |  |  |  | 12
3
4
5
CHALLENGES
1 | Compressor not working properly
2 | Fuel ran out
3
4
Supervisor [Name]: |  |  |  | DALITSO SAKALA
Client's representative [Name]: |  |  |  | SUNGENI TEMBO / CEPHAS NGAZIMBI